MINUTES of the Cirencester Neighbourhood Plan Steering Group meeting held on Wednesday 7th December 2022 at 9:00am via Zoom.

PRESENT:

Brian Hudson, Chair of the Steering Group (Community Representative)

Christina Ibbotson (Community Representative)

Martin Portus (Community Representative) – until 9.45

Nicholas Arbuthnott (Community Representative)

Tony Buxton (Community Representative)

Cllr Nick Bridges (CTC Councillor Representative)

Cllr Jan Gronow (CTC Councillor Representative)

Cllr Nigel Robbins (CTC Councillor Representative)

Andrew Tubb (CEO Cirencester Town Council)

James Brain, (Forward Planning Manager, Cotswold District Council) – until 10.40

Hannah Fountain (Sustainable Transport Manager, Cotswold District Council) – from 9.35

Richard Eastham, Director Feria Urbanism

Officers:  Sian Burke-Murphy, CTC, Project Officer, Corporate Services, Joseph Walker, Community Partnerships Officer (Publica), on behalf of CDC

116.22	Apologies

Jim Grant (Community Representative)

Marco Taylor (Community Representative)

117.22	Absent

Cllr Patrick Coleman (CDC Councillor Representative)

Cllr Sabrina Dixon (Chair of the Cirencester Town Council Climate Change Advisory Group)

118.22	Declarations of Interest

None declared.

119.22	Minutes of the Meeting

The Steering Group received, and approved as an accurate record, the Minutes of the Steering Group meeting held on 5th October 2022.

120.22	Matters Arising

The motion regarding proactive engagement with the Primary Care Surgeries, due to go to CDC for consideration on 16th November, will be followed up. Action: BH.

121.22	SG Review of “Word” Reg14 Draft

The group heard that CI and BH met following the meeting of voting members, which took place on the 27th, to allocate tasks required to complete the draft plan. ACTION: BH to circulate schedule and task list. The aim is to finish full draft by end of January, with-sign off by the SG at its February meeting. However, experience during the next two months may mean that the scale of the task deems this not possible.

There was a discussion around the need for a Primary Residency policy in the NP and JB shared his thoughts as follows:

- There is no evidence currently offered that this is a known issue in Cirencester. Council Tax data suggests Cirencester has fewer 2nd homes and holiday homes nationally than other towns. Cirencester tax liability data (2020) suggests these homes currently make up 2%. Nationally, 20% is the accepted justification for going down this sort of policy route. Further, the NPPF expectation is that we must meet a wide variety of housing needs unless there is justification to deviate from that. JB also suggested that the wider national context is changing and that 2nd homes may form a part of a sensible response to that.

ACTION: BH proposed that any decision on this policy should be put on hold while further work is done at the CDC, further thought is given to this topic both within the SG and at the CDC and to see how current Government planning policy changes manifest themselves

- Even if the data did show a problem, this policy would have strategic implications as 25-30% social need is being met and so the potential is that the NP would be straying into more strategic territory, which would be better met in the Local Plan. JB suggested he could raise it for the Local Plan review as coming from the NP but that he would need evidence to justify it. Action: JB

There was also discussion around the need for a policy addressing multi-occupancy in the NP:

- Key concerns it would address 1) paving over of front gardens for parking 2) the increase in vehicular movement 3) reduction of activity in a key sector of the housing market for second steppers.

- On the contrary, it was pointed out that the NP 20-minute neighbourhood policy encourages mixed communities within each neighbourhood. There is no evidence currently offered that the neighbourhood mix is being detrimentally impacted by multi-occupancy at the level at which it currently exists. JW added to this argument that the current threshold for where multiple occupation can be justifiably impacted in planning is 5 bedrooms.

- AT highlighted recent cases whereby developers and/or property owners have fenced off amenity land to enable additional parking and applied for planning permission - in one case this was approved.

- Taking into account the above points made, JB suggested to the group that the NP could instead include a policy to protect verges and open spaces susceptible to the sort of developer activity highlighted above.

ACTION: AT to provide CDC with a list of verges and open spaces owned by CTC so that when an application comes through, CDC will be aware of ownership.

- JB agreed with the SG concerns over multiple cars and lack of active travel choices being made by students.

ACTION: JB to talk to the promoter of purpose-built student accommodation about a possible meeting with the NPSG to discuss.

As above, it was proposed that any decision on this policy should be put on hold while further work is done at the CDC and further thought is given to this topic both within the SG and at the CDC.

122.22	SG Plan/Schedule for Reg.14/TCMP Consultation

The group received an update from JW that Natural England has now responded to the SEA Screening document and are in agreement with other consultees that it would likely be unnecessary for the NP. JB suggested to the group that we can move forward feeling confident that an SEA will not be required for the CNP.

JB confirmed that CDC will be undertaking an SEA screening on the TCMP too – He will be keeping the NPSG appraised.

123.22	SG Town Centre Masterplan

The group received an update from JB. Mace will be presenting proposals on 12th January – JB hopes to share that presentation with the Programme Board (which includes BH) by the end of December 2022, and other members of the NPSG who have been involved on January 12 and with the wider SG during February 2023.

124.22	SG CDC Sustainable Transport Project

The group received a presentation update from Hannah Fountain, summarising key elements and progress against timescales for each work stream of the CDC’s Sustainable Transport Project.

ACTION: HF to share the presentation slides with the NPSG, including some additional slides and links requested by the group.

125.22	NP update for the community

SBM shared a draft communication piece with the group for feedback. The piece is scheduled to go out before Christmas and will bring members of the community and other stakeholders up to date with activities of the NPSG over the past 12 months.

ACTION: SG members to feedback any comments by Friday 16th December.

126.22	Land West of Kingshill Lane

The NPSG heard an update from SBM on proposed next steps in relation to a potential planning application for 280 homes on Land West of Kingshill Lane.

127.22	Announcements

None

128.22	Date and Time of Future Meetings

In 2023 SG meetings with Feria will move to TUESDAYS and will be held in the C-HUB, Bingham House and via Zoom, 9.15-11.15am.

Scheduled Tuesday dates are as follows:   17th Jan, 14th Feb, 7th Mar, 4th Apr, 2nd May, 6th Jun, 4th Jul, 1st Aug, 5th Sep, 3rd Oct, 7th Nov, 5th Dec

Agenda item for July, October, January and April – Budget update