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Cirencester Neighbourhood Plan Steering Group

MINUTES of the Cirencester Neighbourhood Plan Steering Group meeting held on Tuesday 14th February 2023 at 9:15am via Zoom.

PRESENT:
Brian Hudson, Chair of the Steering Group (Community Representative)
Christina Ibbotson (Community Representative)
Jim Grant (Community Representative) 
Martin Portus (Community Representative) 
Nicholas Arbuthnott (Community Representative)
Tony Buxton (Community Representative)
Cllr Nick Bridges (CTC Councillor Representative) 
Cllr Jan Gronow (CTC Councillor Representative)
Cllr Nigel Robbins (CTC Councillor Representative)
James Brain, (Forward Planning Manager, Cotswold District Council) 
Richard Eastham, Director Feria Urbanism 

Officers:  Sian Burke-Murphy, CTC, Project Officer, Corporate Services, Joseph Walker, Community Partnerships Officer (Publica), on behalf of CDC

1.23	Apologies
Andrew Tubb (CEO Cirencester Town Council) 

2.23	Absent
Cllr Patrick Coleman (CDC Councillor Representative)
Cllr Sabrina Dixon (Chair of the Cirencester Town Council Climate Change Advisory Group)
Marco Taylor (Community Representative) 

3.23	Declarations of Interest
None declared.

4.23	Minutes of the Meeting
The Steering Group received, and approved as an accurate record, the Minutes of the Steering Group meeting held on 7th December 2022.  

5.23	Matters Arising
· BDH reported that the motion regarding proactive engagement with the Primary Care Surgeries to find sites to meet future needs, due to go to CDC for consideration on 16th November, has been delayed. This will be followed up. ACTION: BH.
· CDC Primary Care motion due to go to cabinet in November has been pushed back to later in the Spring 2023.  ACTION: BH to chase it through with Joe Harris. 
· As per December meeting, Primary residency and Multiple occupation policies are on hold for the time being. C/F
· Following discussions at December’s meeting, JB also undertook to raise the topic of Primary Residency for the Local Plan Review as coming from the NP, but emphasized he would need evidence to justify it. ACTION: JB 
· ACTION: SBM to organise a list of verges and open spaces owned by CTC and share with CDC so that when applications comes through, CDC are aware of ownership.
· At December’s meeting, JB agreed with the SG concerns over multiple cars and lack of active travel choices being made by students and took an ACTION to talk to the promoter of purpose-built student accommodation about a possible meeting with the NPSG to discuss. C/F

6.23	Discussion of Feria feedback on the Reg14 plan materials drafted by the Community volunteers
It was acknowledged that Feria had shared initial feedback on the package of materials and the group welcomed the opportunity to discuss the feedback with RE at the planned workshop on the 1st March.

JB requested CDC look at the Economy chapter as it currently stands so that any obvious issues can be addressed.  ACTION: JG to forward to JB
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7.23	Objectives and plan for the workshop on March 1 to agree the process for production of Reg.14 plan
There was much discussion around the focus of the workshop, that being, to ensure a shared understanding of the process for finalising the Reg14 draft and the associated responsibilities for the content. To achieve this, in more detail, it was agreed that the task is to identify and agree answers to the following points:
· Where are we? A brief review of content so far, what it is still needed, why it is needed
· Use of the content supplied by the Steering Group in recent weeks
· How do we find the missing data, generate the missing content 
· Identification of areas of duplication and inconsistency
· Assignment of the tasks of finding/generating the extra content and resolving the duplication and inconsistencies, and the required delivery dates
· Understand the nature and content of next full draft and the date for its production.

Clarification was provided by the Chair of the NPSG, that this workshop is NOT about suggesting new content and other changes as that opportunity would come again once a comprehensive Reg14 draft has been agreed by Feria and members of the SG drafting the content.  It is solely about agreeing the process, roles and responsibilities and timescales.

JW confirmed that the CDC would be able to assist with the mapping requirements.

[bookmark: _Hlk108620010]8.23	Town Centre Masterplan
The group received an update from JB regarding the Town Centre Masterplan as follows:
· Government planning reforms are seeking to dispense with Supplementary Planning Documents, which is what the TCMP was going to be. Therefore, in order to ensure the TCMP has longevity, it makes more sense that it becomes a part of the Local Plan, although if bought into by the SG and the timescales fit, it will also feature prominently in the NP.
· [bookmark: _GoBack]An early draft TCMP has been produced and will be supplemented by an additional viability assessment and an access and movement study in Cirencester being commissioned by CDC, pulling in principles of the CNP and Green to the Core and looking at where parking comes into that now and in the future. At the invitation of the CDC, Marco Taylor has commented on the draft brief for the access and movement study
· JB is proposing a Symposium / pre-consultation all day event for the TCMP involving a wide range of stakeholders. This would be a soft consultation and would then be followed by the more formal joint (if appropriate) NP and TCMP consultation after the summer. The SG will be invited with the date to be confirmed.
· JB was unable to communicate dates when the TCNP could be shared with the full SG or the target consultation date.

9.23	Budget update
The group received and noted the budget report from CTC CEO.  BDH raised a question as to the probability of the additional funding for the NP in 2023/4 being approved.  NR stated that this sum was withing the direct authorisation  limit of the CTC CEO.


10.23	Land West of Kingshill lane
The group received an update from SBM regarding a meeting which has been arranged with the developer to discuss a potential planning application for 280 houses at Land West of Kingshill Lane. The purpose of this meeting is to hear Pegasus present its early stage thinking/designs, and to give CTC Planning Committee, NPSG and Preston PC the opportunity to feedback, to help the developers to align their application as far as it makes sense to do so, with local design codes and relevant emerging and made Neighbourhood Plans.

11.23	Announcements
	None

12.23	Date and Time of Future Meetings
Scheduled Tuesday dates are as follows:   7th Mar, 4th Apr, 2nd May, 6th Jun, 4th Jul, 1st Aug, 5th Sep, 3rd Oct, 7th Nov, 5th Dec

RE informed the group that he is unable to attend the meeting on the 7th March.
Agenda item for July, October, January and April – Budget update
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