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Cirencester Neighbourhood Plan Steering Group

[bookmark: _GoBack]MINUTES of the Cirencester Neighbourhood Plan Steering Group meeting held on Tuesday 13th June 2023 at 9:00am via Zoom.

PRESENT:
Brian Hudson, Chair of the Steering Group (Community Representative)
Christina Ibbotson (Community Representative)
Martin Portus (Community Representative) 
Nicholas Arbuthnott (Community Representative)
Marco Taylor (Community Representative) 
Andrew Tubb (CEO Cirencester Town Council) 
Cllr Andy Jopp (CTC Councillor Representative) 
Cllr Andrea Pellegram (CTC Councillor Representative) from 9:55am
Cllr Patrick Coleman (CDC Councillor Representative)
James Brain, (Forward Planning Manager, Cotswold District Council)
Richard Eastham, Director Feria Urbanism 

Officers:  Sian Burke-Murphy, CTC, Project Officer, Corporate Services, Joseph Walker, Community Partnerships Officer (Publica), on behalf of CDC

34.23	Apologies
Tony Buxton (Community Representative)
Cllr Sabrina Dixon (Chair of the Cirencester Town Council Climate Change Advisory Group)

35.23	Absent
Cllr Nigel Robbins (CTC Councillor Representative)

36.23	Declarations of Interest
None declared.

37.23	Minutes of the Meeting
The Steering Group received, and approved as an accurate record, the Minutes of the Steering Group meeting held on 2nd May 2023.  

38.23	Matters Arising
None

39.23	Jim Grant and Patrick Moylan
Following the sudden and very sad death of Jim Grant the Chair spoke, on behalf of the Steering Group, of the fantastic contribution Jim Grant made to the development of the Cirencester NP. Jim was one of the original community volunteers and the sheer volume and quality of work he has contributed throughout the project, in particular over the past few months, in drafting the detail of Reg14, is astonishing. 

CI, who has worked closely with Jim throughout the process, has contributed words and information (on behalf of the SG), at the request of Jim’s son, for inclusion at the funeral.

The Chair also took the opportunity to acknowledge the extraordinary contributions made by Patrick Moylan, who passed away late last year. Patrick was also an original community volunteer and made contributions throughout his time on the project, including when he was very ill. 

[bookmark: _Hlk108619665]The SG conveyed its huge sense of loss at the passing of these two remarkable people, who always went above and beyond for the benefit of the community.

40.23	Steering Group recruitment
Following the sad deaths of Patrick Moylan and Jim Grant, the number of community volunteers has been reduced to six. 

The ToR states that “The Steering Group consists of up to 12 community representatives…”. 

It was proposed by the Chair, and agreed by the Steering Group, that at this advanced stage of the project, a recruitment process and subsequent induction would be unnecessarily time-consuming and disruptive at a time when the existing group need to be focused on expediting the route to the Reg.14 consultation.

It was therefore agreed that there would be no recruitment of additional community members to the NPSG, with members of the SG happy to continue as they are.

41.23	Reg14 Plan
Feria supplied the updated Reg14 draft on the 8th June, in readiness for the scheduled ‘deep dive’, as per the agreed Pathway.

The Community Volunteers who will be carrying out the Deep Dive on this document, commended RE on the quality and hard work, evident in this latest draft. RE in turn, praised the Community Volunteers for the depth and quality of the work presented to him.

The Deep Dive will be carried out in three half-day sessions on June 20, 21 and 26 to create a “change log” request, to be sent to Feria.
ACTION: Feria to provide a table of illustrations (photos and diagrams) needed, in readiness for the Deep Dive, so that Community Members can allocate who produces each item.
ACTION: Feria to contact JW at CDC about GIS mapping help.

	The Chair proposed the following schedule after the Deep Dive:
· W/C 3rd July – comments back to RE
· RE to produce an updated draft for consideration by the group by end of September.

There followed a discussion about the uncertainties in relation to provision of Primary Care in Cirencester and about what form a generic policy on Primary Care might take. BH reminded the group that RE is drafting a generic policy for inclusion in the Reg14 Plan.
ACTION: RE to draft a generic policy on Primary Care, for consideration by the SG.




42.23	CDC update
JB updated the SG on progress in relation to four feasibility studies, which will be undertaken to inform and evidence the TCMP.

· Cirencester Access and Movement Study – This has been commissioned and will look at parking demand, now and in the future and as a revenue stream for CDC. It will consider different locations and concepts such as park and stride.
ACTION: JB to enable a meeting between SYSTRA (the consultants working with CDC) and the appropriate community volunteers.
· Archaeology Review, by Cotswold Archaeology, will begin end of June and will seek to develop a red, amber, green approach to assessing and mapping the risks associated with each site. It will bring together other archaeology studies which have taken place over the decades.
· Internal Historic Environment Review – Cotswold Conservation Officers are looking at this and JB will share the reviews with BH/NA when they are complete.
· Market and viability assessments – This study is about the financial viability of the TCMP. 

The outcome of these studies, especially 1 and 4 above, will indicate feasibility for implementation of the TCMP in its current form. The aim is to have a steer on this by September 2023.

[bookmark: _Hlk108620010]43.23	Sites for Primary Care
There was a discussion around the inclusion of a generic policy to address Sites for Primary Care within the Neighbourhood Plan, to build upon the contributions made by Patrick Moylan during his time on the SG.

It was noted that additional information would be required to guide this process, concerning principles of delivery of primary care, objectives, aspirations of practices and doctors etc.
	ACTION: RE to draft a generic policy for consideration by the NPSG.

44.23	Announcements
None

45.23	Date and Time of Future Meetings
Scheduled Tuesday dates are as follows:   4th Jul, 1st Aug, 5th Sep, 3rd Oct, 7th Nov, 5th Dec  

Agenda item for July, October, January and April – Budget update
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